## Sheet1
Task Number | Task Name | Status | Completed By | Additional Notes |  | Friday Dec 9, Sync ToDo | Status
1 | Document with team name, group members, and which project you will work on. If the project is your own idea, a requirements document must be submitted and approved. | Complete | Gustavo Gyotoku, Tim Tieng, Peter Broecker | This task was completed as a group through team conversations and brainstorming sessions |  | Update Conceptual Data model to reflect Gustavos Logical Data model | Complete
2 | Data analysis of the facts listing entities, attributes, and relationships in the data model. | Complete | Gustavo Gyotoku, Tim Tieng, Peter Broecker | This task was completed as a group through team conversations and brainstorming sessions |  | Finish Logical Datamodel | In progress
3 | Conceptual data model diagram. | Complete | Gustavo Gyotoku, Tim Tieng, Peter Broecker | Updated based off Gustavo's logical Model progress/comments from Dr.Block |  | Update Script to relfect logical data model | In progress
4 | Logical data model diagram. | In-Progress | Gustavo Gyotoku, Tim Tieng, Peter Broecker | This task was completed through collaborative sessions and feedback loops
5 | Identification of your external data model and data logic. | Complete | Gustavo Gyotoku
6 | Basic layout of all application screens. | Not Started |  |  | look at previous projects for examples
7 | Diagram of each screen used in the application. | Not Started
8 | SQL up/down script to implement the internal model with initial data. | In-Progress | Tim Tieng,
9 | SQL up/down Script to load/migrate in existing data. | In-Progress | Tim Tieng,
10 | SQL up/down script of data logic for the external data model. | In-Progress | Tim Tieng, |  | What the user will see
11 | Implementation of the application itself. | Not Started
12 | A team log recording individual and group contributions to the project, including when and by whom. | Complete | Tim Tieng